CONTRACT AGREEMENT (EXTRACT)

Eastern Corridor Logistics Hub — Package B

Contract SLDC/ECLH/B/2025-014 dated 10/02/2025

Key details

| Customer name: | Sawaed Al Bina Contracting Co. |
| --- | --- |
| CR number: | 2050117342 |
| Project: | P1 Eastern Corridor Logistics Hub — Package B |
| Employer: | Sharqiya Logistics Development Co. (SLDC) |
| Consultant: | Dar Al Mimar Engineering Consultants |
| Contract date: | 10/02/2025 |
| Contract value: | SAR 486,000,000 |
| Advance payment: | 10.0% |
| Retention: | 10.0% |
| Payment of certified amounts within (days): | 56 |
| Commencement date: | 01/03/2025 |
| Completion date: | 31/08/2027 |
| Performance bond: | 10.0% |

The Employer, Sharqiya Logistics Development Co. (SLDC), a company owned by the Eastern Province Development Fund, engages the Contractor to construct Package B (warehouse blocks W1-W6, internal roads and utilities) of the Eastern Corridor Logistics Hub.

Contract price SAR 486,000,000 (lump sum, excluding VAT). Time for completion: 30 months from 01/03/2025, i.e. 31/08/2027.

Advance payment 10% against an advance payment guarantee, recovered at 10% of each interim certificate.

Retention 10% of each interim certificate; half released at taking-over, half at the end of the 12-month defects liability period.

Interim certificates are paid within 56 days of certification by the Engineer. Late payment does not entitle the Contractor to suspend work before 90 days of delay (clause 16.1).

Extensions of time are valid only when approved in writing by the Employer (clause 8.4). Delay damages 0.1% of the contract price per day, capped at 10%.

Performance security 10% of the contract price, valid until the end of the defects liability period.

| ______________________ Eng. Fahd Al-Otaishan, Projects Director Sharqiya Logistics Development Co. (SLDC) | ______________________ Turki Hamad Al-Sawaed Sawaed Al Bina Contracting Co. |
| --- | --- |