INTERIM PAYMENT CERTIFICATE

Eastern Corridor Logistics Hub — Package B · IPC-11

Work up to 28/02/2026 · certified 21/03/2026

Key details

| Customer name: | Sawaed Al Bina Contracting Co. |
| --- | --- |
| CR number: | 2050117342 |
| Project: | P1 Eastern Corridor Logistics Hub — Package B |
| Certificate number: | IPC-11 |
| Work up to: | 28/02/2026 |
| Certified on: | 21/03/2026 |
| Cumulative work done: | SAR 99,896,000 |
| Gross this certificate: | SAR 11,793,000 |
| Retention deducted: | SAR 1,179,000 |
| Advance recovery: | SAR 1,179,000 |
| Net amount payable: | SAR 9,435,000 |
| Cumulative retention: | SAR 9,989,000 |
| Due date: | 16/05/2026 |

| Item | SAR |
| --- | --- |
| Cumulative work done (gross) | 99,896,000 |
| Less: previously certified | 88,103,000 |
| Gross this certificate | 11,793,000 |
| Less: retention (10%) | 1,179,000 |
| Less: advance recovery | 1,179,000 |
| Net amount payable | 9,435,000 |

Payable within 56 days of certification, i.e. by 16/05/2026. Cumulative retention held: SAR 9,989,000.

______________________ Eng. Waleed Mansour The Engineer